## Slide 1
Planning your IATI project
(based on the Netherlands Red Cross open data project)

## Slide 2: Focus of IATI publication
Communication
External obligation
Business intelligence
Transparency
Rode Kruis

## Slide 3: Broad team
Internationale Hulpverlening
Marketing & Fondsenwerving
Webteam
Finance & control
Legal
ICT
Communicatie

## Slide 4: Phases & key questions
Strategy & planning
Mapping the data
Realisation
Publication & Use
September - October
October- November
December- February
Q1 2015
Why you want to publish IATI data?
What do you already know?
About your team
What is an ‘activity’ in your organisation
Reasons not to publish activities
Coverage of activities
Permissions and licenses
What data do you already have?
Where is that data in your organisation now?
What do you need to do to make it suitable for publication (and for your desired outcomes)
Which systems need to change in order to produce the desired IATI data?
Which processes need to change?
Setting up your accounts for
publishing data
Verifying your data
Publishing your data
Based on Netherlands Red Cross project planning

## Slide 5: Choices
Emphasis on desired USE of IATI data “Start with the end in mind”
Produce a ‘prototype’ IATI data set ASAP “Open data is not rocket science” and to manage expectations early

## Slide 7: Overall planning
Strategy & planning
Mapping the data
Realisation
Publication & Use
September - October
October- November
December- February
Q1 2015
Planning IATI publication
Systems/ info assessment
Require-ments analysis
Mapping IATI data
Analyse systems changes
Analyse process changes
Systems changes
Process changes
Test process
Adaptation
Publication
Legal/licenses, Exclusions, Communication planning, …
Based on Netherlands Red Cross project planning

## Slide 8: Tot eind van dit jaar
Strategy & planning
Mapping the data
Realisation
Publication & Use
September - October
October- November
December- February
Q1 2015
Planning IATI publication
Systems/ info assessment
Require-ments analysis
Mapping IATI data
Analyse systems changes
Analyse process changes
Systems changes
Process changes
Test process
Adaptation
Publication
Legal/licenses, Exclusions, Communication planning, …
Based on Netherlands Red Cross project planning

## Slide 9: Plan your own project
Which activities are not relevant for your organisation? (e.g because of the size of your organisation)
Which steps would you add?
What is needed to involve:
  Communication
  The Legal department
  …
Do you think prototyping will work in your organisation?